## Overview
A Multilingual AI Assistant for Accessing Health, Housing, and Schooling Information
12-week plan. Week 1 starts Mon 05 Oct 2026; current week is 4 (highlighted). Task status lives on the Tasks sheet.
Week | Start | End | Theme | Deliverable | Done | Tasks
1 | 2026-10-05 | 2026-10-11 | Scope and research design | Research question, objectives, scope (England), target languages, metrics, ethics pre-screen, repo
2 | 2026-10-12 | 2026-10-18 | Literature and architecture | Verified reading list, system architecture, tool and licence choices
3 | 2026-10-19 | 2026-10-25 | Corpus collection | 38 official pages ingested with raw snapshots and a data card
4 | 2026-10-26 | 2026-11-01 | Chunking, index and retrieval baseline | Section chunks, multilingual FAISS index, 150-query retrieval experiment, failure analysis
5 | 2026-11-02 | 2026-11-08 | Translation layer and retrieval hardening | Jurisdiction filter, language ID, translate-then-retrieve vs direct comparison, verified translations
6 | 2026-11-09 | 2026-11-15 | Grounded answer generation | LLM answers only from retrieved sources with numbered citations, plain-language style, refusal rule
7 | 2026-11-16 | 2026-11-22 | Baseline and evaluation set | Ungrounded LLM baseline, ~100-question gold set incl. unanswerable, scoring rubric, ethics approval
8 | 2026-11-23 | 2026-11-29 | Accessible front-end | Web prototype with language picker, right-to-left support, citation display; participants recruited
9 | 2026-11-30 | 2026-12-06 | Evaluation runs and user study | Grounded vs ungrounded scored; small user study run; corpus re-crawled to measure content drift
10 | 2026-12-07 | 2026-12-13 | Analysis and results write-up | Results and discussion chapters with tables, figures and failure cases
11 | 2026-12-14 | 2026-12-20 | Full draft | Introduction, literature review, method, ethics and limitations chapters; full draft to supervisor
12 | 2026-12-21 | 2026-12-27 | Revision and submission | Supervisor feedback applied, demo video, packaged artefact, final submission
Total

## Tasks
Week | ID | Task | Output / evidence | Status
1 | T01 | Fix research question, aim, objectives and scope (England only; health, housing, schools) | docs/project-scope.md | Done
1 | T02 | Choose target languages from evidence (ONS Census 2021 main languages) | docs/project-scope.md | Done
1 | T03 | Define metrics: retrieval hit@k/MRR, answer accuracy, hallucination rate, citation correctness, comprehension | docs/evaluation-plan.md | Done
1 | T04 | Ethics pre-screen for the user study and draft application | docs/ethics-notes.md | In progress
1 | T05 | Project repo, Python environment, pinned requirements | requirements.txt | Done
2 | T06 | Reading list on RAG, multilingual embeddings, MT and RAG evaluation (all references verified on arXiv) | docs/literature-notes.md | Done
2 | T07 | Architecture: ingest > chunk > embed > index > retrieve > generate > translate > UI | docs/architecture.md | Done
2 | T08 | Tool selection with licences (e5 MIT, MiniLM Apache-2.0, FAISS MIT, NLLB CC-BY-NC-4.0) | docs/architecture.md | Done
2 | T09 | Source licensing check (Open Government Licence v3.0; nhs.uk reuse terms) | docs/data-card.md | Done
3 | T10 | Curate and live-validate source list: 26 GOV.UK + 12 NHS.uk pages | src/sources.py | Done
3 | T11 | Ingestion: GOV.UK Content API + NHS HTML, raw snapshots, fetch timestamp | src/ingest.py | Done
3 | T12 | Handle GOV.UK formats (guide, answer, local_transaction, transaction, detailed_guide) and NHS lead text | src/ingest.py | Done
3 | T13 | Data card: counts per domain, dates, currency caveats (Renters' Rights Act, 1 May 2026) | docs/data-card.md | Done
4 | T14 | Heading-aware chunking (40-200 words, 40-word overlap, title + heading prefix) | src/chunk.py | Done
4 | T15 | Multilingual embeddings (multilingual-e5-base) + FAISS index | src/retrieval.py | Done
4 | T16 | Test set: 30 questions x 5 languages, verbatim answer phrase checked on gold page | eval/queries.csv | Done
4 | T17 | Retrieval experiment: BM25 vs notebook set-up vs e5 sections vs MiniLM sections | results/retrieval_by_lang.csv | Done
4 | T18 | Failure analysis (wrong nation, strict answer phrase, Urdu weakest) | docs/week-04-report.md | Done
4 | T19 | Rebuild week 4 notebook on the project pipeline | notebooks/week04_retrieval.ipynb | Done
4 | T20 | Weekly progress report for supervisor | docs/week-04-report.md | Done
5 | T21 | Tag chunks by UK nation and filter to England by default |  | Not started
5 | T22 | Native-speaker check of pl/ro/ar/ur test questions |  | Not started
5 | T23 | Language identification of the user's question |  | Not started
5 | T24 | NLLB query translation; compare translate-then-retrieve vs direct multilingual retrieval |  | Not started
5 | T25 | Try a reranker on top-20 to close the page-vs-answer gap (hit@3 0.96 vs ans@3 0.67) |  | Not started
6 | T26 | Choose LLM API (multilingual quality, cost, data handling) |  | Not started
6 | T27 | Grounded prompt: answer only from sources, numbered citations with URLs, plain language |  | Not started
6 | T28 | Refusal rule for low retrieval score and out-of-scope questions |  | Not started
6 | T29 | Answer in user's language: LLM direct vs NLLB back-translation |  | Not started
7 | T30 | Ungrounded baseline: same LLM, no retrieved sources |  | Not started
7 | T31 | Gold set to ~100 questions with reference answers, incl. unanswerable ones |  | Not started
7 | T32 | Scoring rubric for accuracy, hallucination, citation correctness; second rater on a sample |  | Not started
7 | T33 | Ethics approval confirmed before any participant contact |  | Not started
8 | T34 | Web front-end: language picker, right-to-left layout, citation cards, last-updated dates |  | Not started
8 | T35 | Accessibility pass (WCAG 2.2 AA basics, plain-language UI copy) |  | Not started
8 | T36 | Recruit user study participants |  | Not started
9 | T37 | Run grounded vs ungrounded on full gold set and score |  | Not started
9 | T38 | User study sessions and comprehension questionnaire |  | Not started
9 | T39 | Re-crawl corpus and measure content drift since week 3 |  | Not started
10 | T40 | Statistics, tables, figures; failure-case catalogue |  | Not started
10 | T41 | Draft results and discussion chapters |  | Not started
11 | T42 | Draft introduction, literature review, method, ethics and limitations |  | Not started
11 | T43 | Full draft to supervisor |  | Not started
12 | T44 | Apply feedback, record demo video, package artefact, submit |  | Not started

## Week 4 results
Retrieval experiment, 150 queries (30 questions x en/pl/ro/ar/ur)
Source: results/retrieval_by_lang.csv. ans@3 = a top-3 chunk contains the verbatim answer phrase (strict lower bound).
System | Language | hit@1 | hit@3 | MRR@10 | ans@3
bm25 | ar | 0.233 | 0.3 | 0.261 | 0.1
bm25 | en | 0.767 | 0.967 | 0.868 | 0.7
bm25 | pl | 0.133 | 0.3 | 0.206 | 0.133
bm25 | ro | 0.133 | 0.133 | 0.171 | 0.1
bm25 | ur | 0.233 | 0.3 | 0.261 | 0.1
e5_naive150 | ar | 0.733 | 0.833 | 0.805 | 0.7
e5_naive150 | en | 0.733 | 0.933 | 0.845 | 0.733
e5_naive150 | pl | 0.667 | 0.933 | 0.801 | 0.6
e5_naive150 | ro | 0.7 | 0.867 | 0.8 | 0.567
e5_naive150 | ur | 0.467 | 0.767 | 0.614 | 0.567
e5_sections | ar | 0.933 | 0.967 | 0.958 | 0.733
e5_sections | en | 0.867 | 1 | 0.933 | 0.767
e5_sections | pl | 0.767 | 1 | 0.878 | 0.7
e5_sections | ro | 0.8 | 0.933 | 0.883 | 0.667
e5_sections | ur | 0.7 | 0.9 | 0.814 | 0.467
minilm_sections | ar | 0.7 | 0.933 | 0.81 | 0.733
minilm_sections | en | 0.867 | 0.967 | 0.916 | 0.8
minilm_sections | pl | 0.7 | 0.933 | 0.812 | 0.6
minilm_sections | ro | 0.767 | 0.967 | 0.864 | 0.667
minilm_sections | ur | 0.733 | 0.9 | 0.826 | 0.567
bm25 | ALL | 0.3 | 0.4 | 0.353 | 0.227
e5_naive150 | ALL | 0.66 | 0.867 | 0.773 | 0.633
e5_sections | ALL | 0.813 | 0.96 | 0.893 | 0.667
minilm_sections | ALL | 0.753 | 0.94 | 0.846 | 0.673

## Risks
Risk | Severity | Evidence | Mitigation
Answer is correct for the wrong UK nation (Scotland/Wales/NI sections) | High | Seen in week 4 (school leaving age) | Tag chunks by nation, filter to England, show jurisdiction in UI (T21)
Official page changes after crawl (e.g. Renters' Rights Act from 1 May 2026) | High | public_updated_at did not reflect the 2026 changes | Store fetch date, show it with every citation, re-crawl and measure drift (T39)
Author-written translations bias the multilingual test set | Medium | All non-English queries unverified | Native-speaker check before reporting final numbers (T22)
Right page retrieved but not the answering section | Medium | hit@3 0.96 vs ans@3 0.67 | Reranker, better chunking, graded relevance judgments (T25, T32)
Ethics approval delays the user study | Medium | Study planned for week 9 | Submit early; fall back to expert review if not approved
NLLB licence is non-commercial | Low | CC-BY-NC-4.0 | Acceptable for research; note in deployment recommendations
Council-specific rules (admissions dates, housing) live on 300+ council sites | Medium | GOV.UK local_transaction pages only redirect | Assistant points users to their council; optional single-council case study